## Qtr 3 Report
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION | : MIMAROPA
| PROVINCE | : PALAWAN | [6 empty] | CALENDAR YEAR | : 2023
| CITY/MUNICIPALITY | : CULION | [6 empty] | QUARTER | : 4
Program or Project |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
A. Consruction of Covered Courts
| 1. Construction Covered Court, Sitio Alava |  | Bgy. Binudac | 4500000 | 06-30-2023 |  | 53.39% | 2402499.08 |  | On-going
| 2. Construction Covered Court, Sitio Pulang Lupa |  | Brgy. Osmeña | 2500000 | 06-30-2023 | 11-17-2023 | 100% | 2486336.09 |  | Completed
| 3. Construction Covered Court, Sitio Rizal |  | Bgy. Tiza | 2500000 | 06-30-2023 |  | 58.23% | 1455720.07 |  | On-going
| 4. Toilet-Zero Defecation Program |  | Municipal Wide | 3000000 | 01-27-2023 | 02-27-2023 | 100% | 3000000 |  | Completed
| 5. IP Housing Program |  | All Barangay | 9000000 |  |  | 14.99% | 1349144.31 |  | On-going
ECONOMIC DEVELOPMENT
| 1. Road Preparation (Osmeña-Burabod) |  | Bgy. Osmeña/Burabod | 5000760.3 | 03-28-2023 | 05-17-2023 | 99.94% | 4997961.86 |  | Completed
| 2. Development Counterpart Fund |  | Municipal Wide | 1500000 | 03-28-2023 | 04-21-2023 | 100% | 1450000 |  | Completed
| 3. Level 3 Water System Program |  | Municipal Wide | 5236027.3
GENERAL DEVELOPMENT
| 1. Solar Electrification |  | Municipal Wide | 6000000 | 03-28-2023 | 04-20-2023 | 100% | 5924500 |  | Completed
| 2. Cultural/Historical Rehabilitation |  | Municipal Wide | 1000000 |  |  | 14.99% | 149916.12 |  | On-going
| 3. Solid Waste Management Program |  | All Barangay | 2485000 | 01-23-2023 | 12-20-2023 | 99.99% | 2484846 |  | Completed
| TOTAL |  |  | 42721787.6 |  |  |  | 25700923.53
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  |  | Flory Velle P. Sotero, CPA |  |  |  | Ma. Virginia N. De Vera
|  |  | Municipal Budget Officer |  |  |  | Municipal Mayor

## Qtr 2 Report
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION | : MIMAROPA
| PROVINCE | : PALAWAN | [6 empty] | CALENDAR YEAR | : 2023
| CITY/MUNICIPALITY | : CULION | [6 empty] | QUARTER | : 3
Program or Project |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
A. Consruction of Covered Courts
| 1. Construction Covered Court, Sitio Alava |  | Bgy. Binudac | 4500000 | 06-30-2023 |  | 53.39% | 2402499.08 |  | On-going
| 2. Construction Covered Court, Sitio Pulang Lupa |  | Brgy. Osmeña | 2500000 | 06-30-2023 |  | 67.7% | 1692453.11 |  | On-going
| 3. Construction Covered Court, Sitio Rizal |  | Bgy. Tiza | 2500000 | 06-30-2023 |  | 58.23% | 1455720.07 |  | On-going
| 4. Toilet-Zero Defecation Program |  | Municipal Wide | 3000000 | 01-27-2023 | 02-27-2023 | 100% | 3000000 |  | Completed
| 5. IP Housing Program |  | All Barangay | 9000000
ECONOMIC DEVELOPMENT
| 1. Road Preparation (Osmeña-Burabod) |  | Bgy. Osmeña/Burabod | 5000760.3 | 03-28-2023 |  | 99.94% | 4997961.86 |  | Completed
| 2. Development Counterpart Fund |  | Municipal Wide | 1500000 | 03-28-2023 |  | 100% | 1450000 |  | Completed
| 3. Level 3 Water System Program |  | Municipal Wide | 5236027.3
GENERAL DEVELOPMENT
| 1. Solar Electrification |  | Municipal Wide | 6000000 | 03-28-2023 |  | 100% | 5924500 |  | Completed
| 2. Cultural/Historical Rehabilitation |  | Municipal Wide | 1000000
| 3. Solid Waste Management Program |  | All Barangay | 2485000 | 01-23-2023 | 12-20-2023 | 83.31% | 2070296 |  | On-going
| TOTAL |  |  | 42721787.6 |  |  |  | 22993430.12
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  |  | Flory Velle P. Sotero, CPA |  |  |  | Ma. Virginia N. De Vera
|  |  | Municipal Budget Officer |  |  |  | Municipal Mayor
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION | : MIMAROPA
| PROVINCE | : PALAWAN | [6 empty] | CALENDAR YEAR | : 2023
| CITY/MUNICIPALITY | : CULION | [6 empty] | QUARTER | : 2
Program or Project |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
A. Consruction of Covered Courts
| 1. Construction Covered Court, Sitio Alava |  | Bgy. Binudac | 4500000 | 06-30-2023 |  |  |  |  | On Bidding process
| 2. Construction Covered Court, Sitio Pulang Lupa |  | Brgy. Osmeña | 2500000 | 06-30-2023 |  |  |  |  | On Bidding process
| 3. Construction Covered Court, Sitio Rizal |  | Bgy. Tiza | 2500000 | 06-30-2023 |  |  |  |  | On Bidding process
| 4. Toilet-Zero Defecation Program |  | Municipal Wide | 3000000 | 01-27-2023 | 02-27-2023 | 100% | 3000000
| 5. IP Housing Program |  | All Barangay | 9000000
ECONOMIC DEVELOPMENT
| 1. Road Preparation (Osmeña-Burabod) |  | Bgy. Osmeña/Burabod | 5000760.3 | 03-28-2023 |  |  | 4498165.75 |  | On-going
| 2. Development Counterpart Fund |  | Municipal Wide | 1500000 | 03-28-2023 |  |  | 1450000 |  | On-going
| 3. Level 3 Water System Program |  | Municipal Wide | 5236027.3
GENERAL DEVELOPMENT
| 1. Solar Electrification |  | Municipal Wide | 6000000 | 03-28-2023 |  | 98.74% | 5924500
| 2. Cultural/Historical Rehabilitation |  | Municipal Wide | 1000000
| 3. Solid Waste Management Program |  | All Barangay | 2485000 | 01-23-2023 | 12-20-2023 | 35.07% | 871586 |  | On-going
| TOTAL |  |  | 42721787.6 |  |  |  | 15744251.75
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  |  | Flory Velle P. Sotero, CPA |  |  |  | Ma. Virginia N. De Vera
|  |  | Municipal Budget Officer |  |  |  | Municipal Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2