## Qtr 1 Report
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION | : MIMAROPA
| PROVINCE | : PALAWAN | [6 empty] | CALENDAR YEAR | 2024
| CITY/MUNICIPALITY | : CULION | [6 empty] | QUARTER | : 1
Program or Project |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
| 1. Canimango High School Multi-Purpose Covered Court |  | Brgy. Galoc | 4500000
| 2. Sitio Palwatan, Brgy. Luac Multi-Purpose Covered Court |  | Brgy. Luac | 2500000
| 3. Zero Defecation Program |  | Municipal Wide | 3500000 | 01/25/2024 | 01/31/2024 | 100% | 3500000 |  | Completed
ECONOMIC DEVELOPMENT
| 1. Culion Water System Level III-Landbank Amortization |  | Bgy. Osmeña/Burabod | 6102739.73 | 11/17/2023 |  | 12.15% | 741706.12 |  | On-going
| 2. San Pedro To Burabod Road Preparation |  | Municipal Wide | 4000000
| 3. Construction of Alava Sea Wall |  | Brgy. Binudac | 2500000
| 4. Binudac Critical Areas road Preparation |  | Brgy. Binudac | 3000000
| 5. Food Basket Complementation Program |  | Municipal Wide | 2500000
| 6. Livelihood Program |  | Municipal Wide | 4500000 | 01/25/2024 | 01/31/2024 | 100% | 4500000 |  | Completed
GENERAL DEVELOPMENT
| 1. Cultural and Historical Rehabilitation Program |  | Municipal Wide | 1000000
| 2. Solar Lights Electrification Program |  | Municipal Wide | 9000000
| 3. Solid Waste Management Program |  | All Barangay | 2227168.27 |  |  | 20.23% | 450450 |  | On-going
| TOTAL |  |  | 45329908 |  |  |  | 9192156.12
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  |  | Flory Velle P. Sotero, CPA |  |  |  | Ma. Virginia N. De Vera
|  |  | Municipal Budget Officer |  |  |  | Municipal Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2